## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Student | 2025-11-01 | OCR failed to correctly recognize Aadhaar number in low-resolution images | Sprint 1 | Student | Functional | Applied image preprocessing and contrast enhancement | 2026-03-03 | Closed | OCR accuracy improved
2 | Student | 2025-11-02 | Incorrect characters extracted for name field | Sprint 1 | Student | Functional | Added text normalization and validation rules | 2026-03-04 | Closed | Reduced OCR errors
3 | Student | 2025-11-03 | Preprocessing script crashed on unsupported image format | Sprint 1 | Student | Technical | Added input format validation | 2026-03-04 | Closed | Handled edge cases
4 | Student | 2025-11-04 | Fraud detection model flagged genuine document as tampered | Sprint 3 | Student | Logical | Tuned classification threshold | 2026-03-06 | Closed | False positives reduced
5 | Student | 2025-11-05 | API failed when no image was uploaded | Sprint 4 | Student | Technical | Added input validation and error handling | 2026-03-06 | Closed | API stabilized
6 | Student | 2025-11-06 | UI did not display fraud score properly | Sprint 4 | Student | UI | Fixed JavaScript rendering logic | 2026-03-07 | Closed | UI updated
7 | Student | 2025-11-07 | Delay in processing large images | Sprint 2 | Student | Performance | Optimized image resolution before OCR | 2026-03-08 | Closed | Processing time reduced

## Sheet2
1️⃣ Logical
Defects caused by incorrect logic, conditions, calculations, or decision flow in the application.
Examples (your project):
Fraud detection flagging genuine Aadhaar as tampered
Incorrect confidence score calculation
2️⃣ User Interface
Defects related to UI layout, alignment, visibility, or user interaction.
Examples:
Fraud score not displayed on frontend
Upload button not responding
3️⃣ Maintainability
Issues that affect code readability, modularity, or future enhancements.
Examples:
Hardcoded Aadhaar validation rules
Poorly structured preprocessing scripts
4️⃣ Standards
Violations of coding standards, documentation guidelines, or project conventions.
Examples:
Missing comments in OCR module
Inconsistent naming conventions
5️⃣ Others
Defects that don’t fit into the above categories.
Examples:
Performance delays
Deployment or environment-related issues